## Sheet1
Freeway Safety and Congestion Relief Program |  | Jurisdiction | Project Status | Completion Year | Measure A Expended | Total Project Cost | Notes
| Bus/Carpool ramp connection from SR 50 E to SR 99 S | Caltrans | Not Initiated | 2037
| I/80 Bus/Carpool Lanes: I-5—Capital City Freeway | Caltrans | Completed | 2017 | 722688 | 136000000 | Project includes Carpool lanes as well as road repair and other items.
| I-5 Bus/Carpool Lanes: Elk Grove to SR 50 | Caltrans | Completed | 2023 | 28555514 | 370000000 | Project includes Carpool lanes as well as road repair and other items.
| I-5 Bus/Carpool Lanes: SR50 to I-80 | Caltrans | Environmental | 2030 | 0 | 453000000 | Project includes managed lanes to Yolo County.
| Ramp widenings for connectors between SR 50 and I-5 | Caltrans | Not Initiated | 2037
| SR 50 Bus/Carpool Lanes: Sunrise to Watt | Caltrans | Completed | 2012 | 32793233 | 100400000
| SR 50 Bus/Carpool Lanes: Watt thru Downtown Sacto. | Caltrans | Construction | 2025 | 23065655 | 487500000 | Project includes Carpool lanes as well as road repair and other items.
| I-5/I-80 Interchange Upgrade & Carpool Lane Connector | Caltrans | Planning | 2035 | 1500000